## Sheet1
stand up meeting date: 01/07/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | continue chat | 4 h |  | continue chat | 4 h | I can't complete task follow my estimate time
|  |  |  | owner post | 3 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | continue create branch with map | 3 h |  | continue create branch with map | 3 h | file ផ្សេង​ class ផ្សេង
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | reset password | 4 h |  | intergrate frontend with backend on card | 3 h | spent time to research
| button switch | 3 h |  | reset password | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | I fixed code on home card | 3 h |  | I will work on intergrate user profile | 3 h | difficult to fix code
| orginize file to be better than before | 4 h
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | payment success | 2 h |  | origazine file | 2 h | don't understand about code
|  |  |  | line one page to one page | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen | logout back end front end | 3 h |  | vilidation login fornt end | 2 h | don't understand about code
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _