## Sheet1
stand up meeting date: 19/06/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | fix code | 40 mn |  | help member to design | 1 h | confuse code
| find out of project flow | 20 mn |  | start code | 1 h | project error(can not open)
| research sth related with project to get connept | 50 mn |  | research about code | 30 mn
| find subtask for each user in sprint1 | 55 mn
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | design entity database (hold data) | 1 h |  | continue to figurate about the code | 1 h | cannot run file frontend well
| search about the tip how to run code from | 30 mn |  | tip of running one more thing discuss with team about the mock up | 30 mn
| figure about the flow of code | 1 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | Design mock-up on User service | 30 mn |  | continues to design mock-up about the check booking | 1 h | NO concept to design
| created posts | 30 mn |  | post card | 30 mn | Try to research that make spend a lot of time
| registered forms | 30 mn |  | history on user servies | 1 h | Confuse roles and wrong design
| user home page | 30 mn
| doin research about the template user services create post | 20 mn
and edit post
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny
| design login form | 30 mn |  | design new feature | 45 nm | don't have idea to design
| research about the new templete | 30 mn |  | design pay | 50 mn | not creative
| design user service switch account | 45 mn |  | research templete to get idea | 30 mn
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen
| Navbar booking User | 1h 30mn |  | Booking User | 2 h | don't have idea to design
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _