## Sheet1
stand up meeting date: 21/06/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | finished the design on the user page with house details info | 1h |  | research related with map and start do the task in api backend | 1 h | difficult to separate back and front end.
| tested project's backend and frontend | 1h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | design layout of view house | 1 h |  | design role for backend | 1 h | Code frontend still not the same cannot find the way for running
| add new table to entity | 30 mn |  | write code | 50 mn
| research map, research QR code | 1 h
| fix folder code frontend | 2h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | designs like user services dashboard | 1 h |  | design admin dashboard | 1 h | No Idea to design
| checking room and research about the process of room checking | 1h |  | checking owner | 30 mn
| looking to understand the coding that teacher provide to understand | 1h |  | chat between user service and user and list of customer | 1 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | designed mock up user service |  |  | continue to understand code and start code |  | difficult to understand code
research information of design and uderstanding of souce code that reacher provided
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | Form payment | 45 mn |  | design dashbord | 1h | No Idea to design
| user service switch account | 30 mn
| user profile | 30 mn
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen
| Navbar booking User | 1h 30mn |  | Create a beautiful post today | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _