## Sheet1
stand up meeting date: 25/06/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | complete feature page | 2h |  | admin chat with owner | 2 h | help member to fix error
| search chat | 3h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | access api to google | 1 h |  | continue to register put google map to feature | 3 h | defficult to pletform code
help team
| user owner can register account | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | design | 1 h |  | vilidation register | 2 h | don't know how to start
| start code back end and front end | 3 h |  | search more on map | 1 h
help team
| research location related map | 1 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | croll left and croll right owner image | 2 h |  | wrtie code front end owner | 3 h | don't clear about right code
| pop up user account done | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | forgot password | 2 h |  | continue to reset password | 2 h | don’t know how to start code
| reset password | 2 h |  | design mock up swich to owner | 1 h | computer គាំង
| watch video related password | 1 h |  | front end with swich to owner | 2 h
search about code
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen | login form front end | 3 h |  | design booking ticket and write front end code | 4 h | code error
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _