## Sheet1
stand up meeting date: 26/06/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | watch video chat | 4 h |  | contunue chat | 4 h | code error
write code again
spent a lot of time to research
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | finish form register | 2 h |  | continue create branch with map | 3 h | migrate database error
| add map to code | 2 h |  |  |  | put relationship wrong
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | finish register vilidation have only one | 2 h |  | continue validation | 1 h | don't have key fo access to map error
| map front end already but wrong | 2 h |  | continue map front end | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | design front end owner | 2 h |  | show detail owner | 3 h | fix code
| pop up edit | 2 h |  |  |  | computer គាំង
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | wrtie code front end owner switch account | 3 h |  | booking user fornt end code | 2 h | defficult to understand code
| watch video related code | 1 h |  |  |  | computer គាំង
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen | booking ticket place | 3 h |  | help team to write code front end switch owner | 2 h
computer គាំង
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _