## Sheet1
stand up meeting date: 27/06/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | watch video chat | 4 h |  | contunue chat | 4 h | code error
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | add map to code | 2 h |  | continue create branch with map | 3 h | include code doesn't work
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | map front end already but wrong | 2 h |  | continue map front end | 3 h
| finish vilidation | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | design front end owner | 2 h |  | show detail owner | 3 h
| pop up edit | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | booking user fornt end code | 3 h |  | design ticket | 1 h | spent time to understand code
|  |  |  | write code front end ticket | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen | booking ticket place | 3 h |  | coding booking frond end | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _