## Sheet1
stand up meeting date: 09/07/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | update code migration data in back end | 5 h |  | finish migrateion in back end | 5 h | jira error
research
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | finish post and api | 4 h |  | payment | 5 h | can't caught money
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | update autotion | 3 h |  | update reset password | 5 h | other file and don't know how to research
| direct map | 3 h |  | and continue map | 3 h | watch youtube but don't understand
login fail
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | comment feedback | 4 h |  | continue comment feedback | 4 h | code error
update code on front end
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | input booking and show it in ticket | 5 h |  | continue to create table booking | 4 h | don't understand flow code
| all information alert to cart on navbar |  |  | get data form back end to display at front end
| can click and show detail and cancel |  |  | get all date to detail | 4 h
| create table booking on back end | 2 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen
| edit dashboard | 4 h |  | vilidation booking | 4 h | don't know how to do
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _