## Sheet1
stand up meeting date: 10/07/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | help member fix error | 2 h |  |  | 5 h | member lost code
| make on migrate data from back end | 4 h |  | complete migrate show pictures room detail |  | so we need to spend most time for fix
after that to do booking process
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | payment of owner | 4 h |  | continue to do it payment | 5 h | stripe can send but not confirm success
hard to convert from vue code to laravel code
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny | updated the file on Auth | 3 h |  | I will completed maps derection | 5 h | I don't know about the process how to make the file connection between maps and card
| research about the maps direction different files. | 3 h |  | search location | 3 h | spend a lot of time to search and stuck code
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim | comment feedback | 4 h |  | continue comment feedback | 4 h | code error
update code on front end
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | create table booking in back end already | 4 h |  | get data from back end to show on front end | 4 h | can not caught id booking
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen
| Validation User booking | 4 h |  | I installed software for DevOps to research how to use it | 4 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _