## Sheet1
stand up meeting date: 11/07/2024
Team's name | Inns Rest System
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Nay Dany | intergrate data backend | 4 h |  | user booking detail | 5 h | confuse concept of user booking
| owner comfirm booking | 3 h |  | make condition to user book | 3 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Sin Sopanha | I integrate payment with house | 4 h |  | I continue to do it | 5 h | hard to use ajax for pushing my data into the route
some route is not work even if I make the same flow like the route which is works
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Mao Vanny |  | 3 h |  |  | 5 h
|  | 3 h |  |  | 3 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Savvichhika Prim |  | 4 h |  |  | 4 h
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ma Ny | pop up user booking | 4 h |  | pop up ticket | 4 h | code defficult
| pop up ticket notification | 3 h |  | create data in back end and get to desply front end | 4 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Soeum Chen
|  | 4 h |  |  | 4 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _