## Sheet1
Stand up meeting date: 16/12/ 2023
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Voeun Chanthou | add product | 2h30mn | 2h | add categories | 2h30mn
—————————————————————————————-
Mao Vanny | search on order card | 4h | 1:30mn | display card to product | 6h
| fix code in cateories | 3h | 3h | js on Customer order | 3h
—————————————————————————————-
Ma Ny | disply user | 3h | 3h | fix code | 1h
Stand up meeting date: 17/12/ 2023
Voeun Chanthou | add categories | 2h30h | 2h | remove categories | 3h
|  |  |  | add product (fix code) | 1h30mn
—————————————————————————————-
Mao Vanny | display card to product | 6h | 4h | fix some code | 2h
| js on Customer order | 3h | 3h
___________________________________________________________
Ma Ny