## Sheet1
Stand up meeting date: 12/ 12/ 2023
What did they do yesterday? |  |  | What you will do today?
List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Voeun Chanthou | delete card from list | 2h | 1h | add product | 2h 30mn
| total price | 2h | 2h
—————————————————————————————-
Vanny Mao | fix code categories from
write js on product form to display on card product
|  | 4h | 3h | search on order card | 4h
|  | 5h | 5h
—————————————————————————————-
Ny Ma | correct code of payment | 2h |  | search more | 30 mn