## Sheet1
Stand up meeting date: 18/12/ 2023
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Voeun Chanthou | add product | 1h30mn | 1h | make history | 1h
___________________________________________________________
Mao Vanny | fix some code error | 2h | 4h | deshboard on js | 3h
|  |  |  | clearn code on css | 4h
___________________________________________________________
Ma Ny | design deshboard on figma | 1h | 1h
| create slide prepar for presentation | 1:30 mn | 1h
Stand up meeting date: 19/12/ 2023
|  |  |  | delete history | 30mn
Voeun Chanthou | make history | 1h | 1h | do dashboard page | 2h
|  |  |  | delete categorie | 30mn
|  |  |  | final coding (merge) | 2h30mn
___________________________________________________________
Mao Vanny | deshboard on js | 3h | 3h
| clearn code on css | 4h | 4h
___________________________________________________________
Ma Ny | fix bug | 1h |  | prepar presentation