## Sheet1
stand up meeting date: 12/06/2024
Team's name | LARAVEL_FACEBOOK_API-A1
Member's name | What did they do yesterday? |  |  | What will they do today? |  | Probem
| List down the task | Estimate time to fisnish | Actual finish time | List down the task | Estimate time to fisnish
Chanthou Veoun | create post | 30 mn |  | As a user, I want to add friend | 1 h
| update post | 10 mn |  | As a user, I want upload my profile account | 1 h
| delete post | 10 mn
| show post | 10 mn
| show one post | 20 mn
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ __ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ __ |  | _ _ _ _ _ _ _ __
Nearday Loem | register account | 1 h |  | As user, I want to view my profile | 1 h | Computer crash
|  |  |  | As user, I want to edit profile | 1 h
| _ _ _ _ _ _ _ _ _ _ _ _ | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _
Ny Ma | login account | 30 mn |  | create comment | 30 mn
| logout account | 40 mn |  | update commend | 30 mn
|  |  |  | delete comment | 30 mn
|  |  |  | show comment | 30 mn
| _ _ _ _ _ _ _ _ _ _ _ _ |  |  | _ _ _ _ _ _ _ _ _ _ _ _ |  | _ _ _ _ _ _ _ _ _ _ _ _